## OJEU_Open_No_PIN
Tender Timetable - OJEU Open Procedure |  |  |  | Cabco Dates
2004-09-03
| Contract Title: |  |  | 2004-09-17
Responsibilities:
| Highlight Actions as follows - | Department
2004-10-01
ACTION |  | NOTES | DATE | 2004-10-15
2004-10-29
1 | Agree Procurement Route & Responsibilities |  |  | 2004-11-12
2 | Completion of Tender Documents | allow min of 2 weeks | 1900-01-13 | #REF!
3 | Issue Advert to OJEU | 1 day after 2 | 1900-01-14 | #REF!
4 | Advertise in Press (if appropriate) | 2 days after 3 | 1900-01-16 | #REF!
5 | Advertise on Contracts finder, CBC Contract register & Source Leicestershire | 2 days after 3 | 1900-01-16 | #REF!
6 | Email advert to identified prospective companies | 2 day after 3 | 1900-01-16 | #REF!
7 | Tender Documents available until | approx 2 wks before 10 | 1900-02-04 | #REF!
8 | Questions deadline | approx 10 days before 10 | 1900-02-08 | #REF!
9 | Answers deadline | approx 1 wk before 10 | 1900-02-11 | #REF!
10 | Tender Return Date | 35 days from 5 (reduce to 30 days is using Delta electronic tendering suite) | 1900-02-18 | #REF!
11 | Evaluate tenders | allow up to 4 wks | 1900-03-18 | #REF!
12 | Agree short-list | allow at least 3 days | 1900-03-21 | #REF!
13 | Financial checks by Accountancy | allow 1 wk | 1900-03-28
14 | Issue short-list invites (if required) | allow at least 1 wk notice | 1900-04-04
15 | Short-list Presentations (if required) | allow at least 1 wk | 1900-04-11 | #REF!
16 | Further clarification if required | allow at least 1 wk | 1900-04-18
17 | Agree preferred supplier | allow at least 3 days | 1900-04-21
18 | Notify Sucessful & Unsucessful Suppliers | (Alcatel Judgement) | 1900-04-22
19 | 10 day standstill (alcatel period) | Allow 10 days (final day of Alcatel period must be a week day, i.e. if day 10 falls on a Sunday you must carry over to the following Monday) | 1900-05-02
20 | Contract start date | earliest possible | 1900-05-03