## OJEU_Restricted_No_PIN
Tender Timetable - OJEU Restricted Procedure |  |  |  | Cabco Dates
2004-09-03
| Contract Title: |  |  | 2004-09-17
Responsibilities:
| Highlight Actions as follows - | Department
2004-10-01
ACTION |  | NOTES | DATE | 2004-10-15
2004-10-29
1 | Agree Procurement Route & Responsibilities |  |  | 2004-11-12
2 | Completion of PQQ Documents | allow min of 2 weeks | 2012-01-01 | #REF!
3 | Issue Advert to OJEU | 1 day after 2 | 2012-01-03 | #REF!
4 | Advertise in Press (if appropriate) | 2 days after 3 | 2012-01-05 | #REF!
5 | Advertise on Contracts Finder, CBC contract register & Source Leicestershire | 2 days after 3 | 2012-01-05 | #REF!
6 | Email advert to identified prospective companies | 2 days after 3 | 2012-01-05 | #REF!
7 | Documents available until | approx 2 wks before 10 | 2012-01-19 | #REF!
8 | Questions deadline | approx 10 days before 10 | 2012-01-23 | #REF!
9 | Answers deadline | approx 1 wk before 10 | 2012-01-26 | #REF!
10 | Return date for PQQ | allow 30 days from 3 | 2012-02-02 | #REF!
11 | Evaluation & clarification of PQQ | allow up to 4 wks | 2012-03-01 | #REF!
12 | Financial checks by Accountancy | allow 2 wks | 2012-03-15 | #REF!
13 | Agree potential tender list | allow 3 days | 2012-03-18 | #REF!
14 | Issue Successful & Unsucesful short-list invitations | allow at least 1 wk standstill notice after letters sent | 2012-03-19
15 | Completion of Tender Documents | allow 2 wks from completion of PQQ documents | 2012-01-15
16 | Issue tenders | 1 week after 14 | 2012-03-27
17 | Questions deadline | approx 10 days before 19 | 2012-04-16
18 | Answers deadline | approx 1 wk before 19 | 2012-04-19
19 | Tender Return Date | allow 30 days | 2012-04-26
20 | Evaluation & clarification of Tenders | allow 4 wks | 2012-05-24
21 | Agree preferred supplier | allow 3 days | 2012-05-27
22 | Notify Sucessful & Unsucessful Suppliers | (Alcatel Judgement) | 2012-05-28
23 | 10 day Standstill period (alcatel) | Allow 10 days (final day of Alcatel period must be a week day, i.e. if day 10 falls on a Sunday you must carry over to the following Monday) | 2012-06-07
24 | Contract start date | earliest possible | 2012-06-08