## Non_OJEU_Open
Tender Timetable - Non OJEU Open Procedure |  |  |  | Cabco Dates
2004-09-03
| Contract Title: |  |  | 2004-09-17
Responsibilities:
| Highlight Actions as follows - | Department
2004-10-01
ACTION |  | NOTES | DATE | 2004-10-15
2004-10-29
1 | Agree Procurement Route & Responsibilities |  |  | 2004-11-12
2 | Submission of Specification/Requirements to Central Procurement Team (CPT)
3 | Completion of Tender Documents and evaluation matrix | allow min of 2 weeks | 1900-01-13 | #REF!
4 | Advertise on Contract Finder, CBC Contract Register & Source Leicestershire | allow 1 day after 3 | 1900-01-14 | #REF!
5 | Advertise in press (if appropriate) | allow 1 day after 4 | 1900-01-15 | #REF!
6 | Email advert to identified prospective companies | Once adverts have been published (usually within 48hrs of step 4) | 1900-01-17 | #REF!
7 | Tender Documents available until | approx 2 weeks before 10 | 1900-01-28 | #REF!
8 | Questions deadline | 7 days before 10 | 1900-02-04 | #REF!
9 | Answers deadline | 6 days before 10 | 1900-02-05 | #REF!
10 | Tender Return Date | ideally 28 days, no less than 14 days from 4 | 1900-02-11 | #REF!
11 | Evaluation & Clarification of tenders | allow up to 2 wks from step 10 | 1900-02-25 | #REF!
12 | Financial checks by Accountancy | allow up to 1 wk | 1900-03-04 | #REF!
13 | Agree preferred supplier | allow 1 day | 1900-03-05 | #REF!
14 | Notify Successful Supplier & Unsucessful Suppliers | allow 1day | 1900-03-05
15 | Allow 10 day standstill (Alcatel period) from date of notification (not mandatory at this level of expediture) | allow 10 day standstill from step 14 - the standstill must end on a weekday. (i.e. if the 10 day standstill ends on a Sunday you must extend the end date to the following Monday) | 1900-03-15
16 | Contract start date | earliest possible | 1900-03-16