## A3
Draw No. | Site name | scheduled for this year | Date completed this year
1 | BURTON ON THE WOLDS - From OS 71 Melton Road to OS 23 Brook Street- TO BE DONE TWICE A YEAR. | September'20 | 2020-09-04
2 | WYMESWOLD (part 1 of 2)-from 117 Brook St to 64 Brook St- TO BE DONE TWICE A YEAR | October'20 | 2020-09-09
3 | WYMESWOLD (Part 2 of 2) - from RO 13 Swift's Close to London Lane- TO BE DONE TWICE A YEAR | October'20 | 2020-09-09
4 | BARKBY (Part 1 of 2) - from Brookside to Barkby Holt Lane | February'21
5 | BARKBY (Part 2 of 2) - from Main Street to Barkby Lane | March'21 |  | up to farmers field
6 | QUENIBOROUGH - Syston Road to Melton Road | March'21 | 2020-11-05
7 | COSSINGTON (Part 1 of 2) - OS 17 & 23 Middlefield Road | March'21 | 2020-09-09
8 | COSSINGTON (Part 2 of 2) - Derries Nursery | March'21 | 2020-10-06
9 | THURMASTON - From Patterdale Road to railway line | February'21
10 | SHEPSHED (Part 1 of 4) - From Abbey Close to Ashby Road and through the factories | November'20 | 2020-09-24
11 | SHEPSHED (Part 2 of 4) - From RO 42 Cambridge St to factory & 2 Storage Areas | November'20 | 2020-09-27
12 | SHEPSHED (Part 3 of 4) - From factory on Sullington Rd to RO Church on Charnwood Rd | November'20 | 2020-09-28
13 | SHEPSHED (Part 4 of 4) - From RO The Meadows to grill at Glenmore Park | November'20 | 2020-09-29
14 | LOUGHBOROUGH- Old Black Brook (Part 1 of 2) - From Maxwells pub to Dishley Mill | April'21
15 | LOUGHBOROUGH- Old Black Brook (Part 2 of 2) - From Derby Road to the new Black Brook | April'21
16 | LOUGHBOROUGH- Charnwood Water - Access off Tuckers Road | April'21 | 2020-10-28
17 | REARSBY - From RO 13 Brookside to the Rearsby Brook | March'21 | 2020-11-05
18 | SILEBY - From RO 74 to 108 Ratcliffe Road, access through cemetery | March'21 | 2020-10-20
19 | WOODHOUSE - From end of School Lane to end of large pond | March'21 | 2020-10-13
20 | LOUGHBOROUGH - Nanpantan Sports Ground | February'21
21 | LOUGHBOROUGH - Side of Old Ashby Road, from junction with Ravensthorpe Drive to the Shortcliff Brook | March'21 | 2020-10-14
22 | LOUGHBOROUGH - From pathway to grid on Abberton Way | March'21
23 | NEWTOWN LINFORD - From SO 400 Bradgate Rd to grill in farmers field, & Storage Area at RO 412 Bradgate Rd | December'20 | 2020-10-06
24 | NEWTOWN LINFORD - Ditch at SO Bradgate Road, opposite Bradgate Park | December'20 | 2020-10-06
25 | LOUGHBOROUGH - Grange Park/ Allendale Road
26 | LOUGHBOROUGH - Moat Brook - From Moat House to Bradgate Rd & ditch at RO Priory Rd | March'21 | 2020-10-28
27 | QUORN - Ditch at RO 113 & 115 Leicester Rd, access is through Woodside Farm, off Wood Lane | March'21 | 2020-10-14
28 | LOUGHBOROUGH - From end of Kirkstone Drive to boundary hedge in field | March'21 | 2020-11-05
29 | HATHERN - S/O Golden Square | October'20 | 2020-10-01
30 | HATHERN - S/O Garendon Avenue | October'20 | 2020-10-01
31 | HATHERN- S/O Hunts Orchard- Farmers Field |  | 2020-09-30
32 | LOUGHBOROUGH – S/O golf course on Poplar Road | March'21
33 | SYSTON- Barkby Road to Barkby Brook | April'21